## Summary
Resource Productivity report
Project Code & Name: SC180: EPC DESIGN AND CONSTRUCTION OF KHASAB - DABA ASPHALT ROAD AND LINK TO LIMA | [6 empty] | For the month
[7 empty] | Work days | 26
1. Manpower Utilization |  |  | Budgeted for the Work Performed |  | Actual deployment
Sl# | Trade | MM Rate | Man-days | Nos | Man-days | Nos | % Utilization | Cost implication (RO)
1 | Steel Fitter |  | 624 | 24 | 624 | 24 | 100% | 0 | 24 | 0
2 | Carpenter |  | 1274 | 49 | 1274 | 49 | 100% | 0 | 49 | 0
3 | Mason |  | 806 | 31 | 806 | 31 | 100% | 0 | 31 | 0
4 | Helpers |  | 1419.5298 | 54.5973 | 1326 | 51 | 107.1% | 0 | 58 | -7
5 | Driver / Operators |  | 5009.4055 | 192.6694 | 4335.7 | 166.7577 | 115.5% | 0 | 33 | 45
6 | Operator |  | 0 | 159.1388 | 0 | 143 | 111.3% | 0
| Total |  | 9132.9354 | 510.4055 | 8365.7 | 321.7577 | 109.2% | 0 | 195 |  | Total
[9 empty] | 50 |  | Others(Ac tech, Chain men, Electrician, mech )
2. Equipment Utilization |  |  | Budgeted for the Work Performed |  | Actual deployment
Sl# | Lead Equipment | Avg. Eq. Rate /Day | Eqpt Days | Nos | Eqpt Days | Nos | % Utilization | Cost implication (RO)
1 | JCB |  | 52 | 2 | 52 | 2 | 100% | 0
2 | Shovel |  | 268.6667 | 10.3333 | 286 | 11 | 93.94% | 0
3 | Dozer |  | 1035.0297 | 39.8088 | 806 | 31 | 128.4% | 0
4 | Excavator |  | 2401.5439 | 92.3671 | 2314 | 89 | 103.8% | 0
5 | Tipper |  | 590.6133 | 22.7159 | 513.7 | 19.7577 | 115% | 0
6 | Trailer Tipper |  | 0 | 0 | 0 | 0 | 0% | 0
7 | Grader |  | 203.184 | 7.8148 | 130 | 5 | 156.3% | 0
8 | Vibratory Roller |  | 177.184 | 6.8148 | 130 | 5 | 136.3% | 0
9 | Paver |  | 0 | 0 | 0 | 0 | 0% | 0
10 | Tyre Roller |  | 0 | 0 | 0 | 0 | 0% | 0
11 | Tandem Roller Heavy |  | 0 | 0 | 0 | 0 | 0% | 0
12 | Tandom Roller-Medium |  | 0 | 0 | 0 | 0 | 0% | 0
13 | Bitumen Sprayer |  | 0 | 0 | 0 | 0 | 0% | 0
14 | Hiab (Crane Mounted Truck), 7 ton |  | 0 | 0 | 0 | 0 | 0% | 0
15 | Skid tyre loader |  | 26 | 1 | 26 | 1 | 100% | 0
16 | Mobile crane |  | 52 | 2 | 52 | 2 | 100% | 0
17 | Hiab |  | 26 | 1 | 26 | 1 | 100% | 0
18 | Water Tanker |  | 177.184 | 6.8148 | 0 | 0 | 0% | 0
| Total |  | 5009.4055 | 192.6694 | 4335.7 | 166.7577 |  | 0
3. Activity production and productivity
Activty Ref # | Activity | Unit | Commodity Production |  | Productivity - equipment oriented works |  |  | Productivity - man-power oriented works
|  |  | Plan | Actual | Lead equip. | Budgeted Qty./Equp-day | Actual productivity/ man-day | Budgeted Qty./man-day | Actual productivity/ man-day
1 | Access road | Cum | 1155.5556 | 320 | Excavator | 24 | 1.1189
0 | Borrow Screening | Cum | 0 | 0 | #REF! | ` | 0
0 | Unclassified excavation-Hauling & compaction | Cum | 0 | 0 | #REF! | 0 | 0
0 | Unclassified excavation-Cut & Dispose | Cum | 0 | 0 | #REF! | 0 | 0
0 | Subgrade preparation in cut | Cum | 0 | 0 | #REF! | 0 | 0
0 | Unclassified structural excavation (depth ≥ 4.0m) | Cum | 0 | 0 | #REF! | 0 | 0
0 | GSB (Class B)-Extraction and Screening | Cum | 0 | 0 | #REF! | 0 | 0
0 | GSB (Class B)-Hauling and compaction | Cum | 0 | 0 | #REF! | 0 | 0
0 | ABC (Class A)-Extraction and Screening | Cum | 0 | 0 | #REF! | 0 | 0
0 | ABC (Class A)-Crushing | Cum | 0 | 0 | #REF! | 0 | 0
0 | ABC (Class A)-Production, Hauling and Compaction | Cum | 0 | 0 | #REF! | 0 | 0
0 | Bituminous prime & tack coat | Cum | 0 | 0 | #REF! | 0 | 0
0 | BBC -Extraction and Screening | Cum | 0 | 0 | #REF! | 0 | 0
0 | BBC - Crushing | Cum | 0 | 0 | #REF! | 0 | 0
0 | BBC - Production, Laying and Compaction | Cum | 0 | 0 | #REF! | 0 | 0
0 | BWC - Extraction and Screening | Sqm | 0 | 0 | #REF! | 0 | 0
0 | BWC - Crushing | Cum | 0 | 0 | #REF! | 0 | 0
0 | Bituminous Wearing Course - GABRO SHIFTING | Cum | 0 | 0 | #REF! | 0 | 0
0 | BWC - Production, laying and Compaction | Cum | 0 | 0 | #REF! | 0 | 0
0 | Surface milling (up to 50mm thick) | Sqm | 0 | 0 | #REF! | 0 | 0
0 | Sand collection from BNRP | Cum | 0 | 0 |  |  |  | 0 | 0
0 | Road marking/International roughness index. | Sqm | 0 | 0 |  |  |  | 0 | 0
0 | Concrete Class 37.5/20 MS7- Box Culvert. | Cum | 0 | 0 |  |  |  | 0 | 0
0 | Concrete, 50/20 MS7 in "I" Girders for Wadi Bridges | Cum | 0 | 0 |  |  |  | 0 | 0
0 | Concrete, 50/20 Box Girders etc | Cum | 0 | 0 |  |  |  | 0 | 0
0 | Concrete, 50/20 Duck Slab Wadi Bridge | Cum | 0 | 0 |  |  |  | 0 | 0
0 | Concrete Class 45/20 MS7 in Bridge abutment, cap, etc. (Wadi Bridge) | Sqm | 0 | 0 |  |  |  | 0 | 0
0 | HYSD for Structures-Cutting, bending & Tying | MT | 0 | 0 |  |  |  | 0 | 0
0 | Prestressing Cables - 0.6" Diameter Strands Grade 270 | MT | 0 | 0 |  |  |  | 0 | 0
0 | Spherical Bearing | Nos | 0 | 0 |  |  |  | 0 | 0
0 | Bitumen Water proofing Culvert | Sqm | 0 | 0 |  |  |  | 0 | 0
0 | Water Proofing Membrane | Sqm | 0 | 0 |  |  |  | 0 | 0
0 | Abrasion resistant paint system for wadi bridge | Sqm | 0 | 0 |  |  |  | 0 | 0
0 | Gantry & Sign Board | Sqm | 0 | 0 |  |  |  | 0 | 0
0 | Mechanically Stabilized Earth Retaining Walls (MSERWs)-Casting | Sqm | 0 | 0 |  |  |  | 0 | 0
0 | Mechanically Stabilized Earth Retaining Walls (MSERWs)-Erection | Sqm | 0 | 0 |  |  |  | 0 | 0
0 | Precast Concrete barrier, Single face -Casting | Rmt | 0 | 0 |  |  |  | 0 | 0
0 | Precast Concrete barrier, Single face -Erection | Rmt | 0 | 0 |  |  |  | 0 | 0
0 | Raft Heavy Duty Concrete barrier, Single face for Pier Protection | Rmt | 0 | 0 |  |  |  | 0 | 0
0 | Wall Heavy Duty Concrete barrier, Single face for Pier Protection | Rmt | 0 | 0 |  |  |  | 0 | 0
0 | Paint Heavy Duty Concrete barrier, Single face for Pier Protection | Rmt | 0 | 0 |  |  |  | 0 | 0
0 | 2way 100mm dia uPVC duct bank for street lighting cables. | Rmt | 0 | 0 |  |  |  | 0 | 0
0 | 4way 100mm dia uPVC duct for Telephone Cble | Rmt | 0 | 0 |  |  |  | 0 | 0
0 | Structural Backfilling | Cum | 0 | 0 |  |  |  | 0 | 0
0 | Preparation of formation of embankment | Cum | 0 | 0 |  |  |  | 0 | 0
0 | Median filling/Structural back filling | Cum | 0 | 0 |  |  |  | 0 | 0
0 | Preparatory works-Day work | Sum | 0 | 0 |  |  |  | 0 | 0
0 | Structure Miscellaneous works | Sum | 0 | 0 |  |  |  | 0 | 0
0 | Preliminaries-Mobilization | Sum | 0 | 0 |  |  |  | 0 | 0
0 | Preliminaries-Time Related (Maintenance of facilities) | Sum | 0 | 0 |  |  |  | 0 | 0
0 | Reflected Road Stud | #REF! | 0 | 0 |  |  |  | 0 | 0
0 | Gabion Works | #REF! | 0 | 0 |  |  |  | 0 | 0
0 | Trench Excavation & Back filling | #REF! | 0 | 0 |  |  |  | 0 | 0
0 | RIPRAP | #REF! | 0 | 0 |  |  |  | 0 | 0
0 | Curb | #REF! | 0 | 0 |  |  |  | 0 | 0
0 | Bridge Load Test | #REF! | 0 | 0 |  |  |  | 0 | 0
0 | Impact Attenuator | #REF! | 0 | 0 |  |  |  | 0 | 0
|  |  | 0 | 0 |  |  |  | 0 | 0

## PR for MP and Eqt
| Manpower & Equipment- Performance Report | [17 empty] | 0.19231
S.No. | Resource/ Activity | Resource Name & Activity Description | Unit | Productivity Norms |  |  | Plan for the Month |  |  |  | Actuals for the Month |  |  |  | Plan for the week |  |  |  | Actuals for the Week |  |  |  | Remarks/Justification for deviation in Norms
|  |  |  | Budget | Projection(as per site condition) | Actuals FTM | Quantity-FTM | Budget Days | Planned Days | % of Utlz'n | Quantity-FTM | Budget Days | Actual Days | % of Utlz'n | Quantity - FTW | Budget Days | Planned Days | % of Utlz'n | Quantity - FTW | Budget Days | Actual Days | % of Utlz'n
1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 1000% | 8 | 9 | 10 | 1100% | 11 | 12 | 13 | 1400% | 15 | 16 | 17 | 18
1 |  | Access road | m | 24 | 12.2407 | 1.1189 | 1200 | 193.061 | 193.061 | 100% | 320 | 51.4829 | 546 | 9.429% | 230.7692 | 37.1271 | 37.1271 | 100% | 70 | 11.2619 | 126 | 8.938%
| HLP | Helpers | days | 14.6889 | 14.6889 | 2.0513 | 1200 | 81.6944 | 81.6944 | 100% | 320 | 21.7852 | 156 | 13.96% | 230.7692 | 15.7105 | 15.7105 | 100% | 70 | 4.7655 | 36 | 13.24% | Only Daba in prrogress and Lima Salvage operation and cleaning in progress/
| EXV | Excavator | days | 12.2407 | 12.2407 | 1.1189 | 1200 | 98.0333 | 98.0333 | 100% | 320 | 26.1422 | 286 | 9.141% | 230.7692 | 18.8526 | 18.8526 | 100% | 70 | 5.7186 | 66 | 8.665%
| DZR | Dozer | days | 90 | 90 | 3.0769 | 1200 | 13.3333 | 13.3333 | 100% | 320 | 3.5556 | 104 | 3.419% | 230.7692 | 2.5641 | 2.5641 | 100% | 70 | 0.77778 | 24 | 3.241%
2 |  | Unclassified Excavation | Sum | 300 | 300 | 464.4953 | 294439 | 3294.9126 | 3294.9126 | 100% | 277768.2 | 4034.2524 | 3250 | 124.1% | 169868.6538 | 822.38 | 822.38 | 100% | 140427 | 679.845 | 750 | 90.65% |  | 9472 | 15.38%
| HLP | Helpers | days | 300 | 300 | 395.6812 | 294439 | 981.4633 | 981.4633 | 100% | 277768.2 | 925.894 | 702 | 131.9% | 56622.8846 | 188.7429 | 188.7429 | 100% | 46809 | 156.03 | 162 | 96.31% |  | 51757
| EXV | Excavator | days | 120 | 120 | 142.4452 | 294439 | 2453.6583 | 2453.6583 | 100% | 277768.2 | 2314.735 | 1950 | 118.7% | 56622.8846 | 471.8574 | 471.8574 | 100% | 46809 | 390.075 | 450 | 86.68% |  | 48250
| DZR | Dozer | days | 350 | 350 | 464.4953 | 294439 | 841.2543 | 841.2543 | 100% | 277768.2 | 793.6234 | 598 | 132.7% | 56622.8846 | 161.7797 | 161.7797 | 100% | 46809 | 133.74 | 138 | 96.91% |  | 109479
3 |  | Embankment Filling | Sum | 500 | 500 | 1135.7949 | 86379 | 172.758 | 172.758 | 100% | 177184 | 354.368 | 260 | 136.3% | 33222.6923 | 66.4454 | 66.4454 | 100% | 26416 | 52.832 | 60 | 88.05% |  |  | 15.38%
| HLP | Helpers | days | 500 | 500 | 486.7692 | 86379 | 172.758 | 172.758 | 100% | 88592 | 177.184 | 182 | 97.35% | 16611.3462 | 33.2227 | 33.2227 | 100% | 13208 | 26.416 | 42 | 62.9% |  | 22816
| DZR | Dozer | days | 500 | 500 | 1135.7949 | 86379 | 172.758 | 172.758 | 100% | 88592 | 177.184 | 78 | 227.2% | 16611.3462 | 33.2227 | 33.2227 | 100% | 13208 | 26.416 | 18 | 146.8% |  | 3400
| MGR | Grader | days | 500 | 500 | 851.8462 | 86379 | 172.758 | 172.758 | 100% | 88592 | 177.184 | 104 | 170.4% | 16611.3462 | 33.2227 | 33.2227 | 100% | 13208 | 26.416 | 24 | 110.1% |  | 50690
| RVB | Vibratory Roller | days | 500 | 500 | 681.4769 | 86379 | 172.758 | 172.758 | 100% | 88592 | 177.184 | 130 | 136.3% | 16611.3462 | 33.2227 | 33.2227 | 100% | 13208 | 26.416 | 30 | 88.05%
| TPR | Tipper | days | 150 | 150 | 172.4586 | 86379 | 575.86 | 575.86 | 100% | 88592 | 590.6133 | 513.7 | 115% | 16611.3462 | 110.7423 | 110.7423 | 100% | 13208 | 88.0533 | 113.7 | 77.44% |  | 76906
| BWT | Water Tanker | days | 500 | 500 | 0 | 86379 | 172.758 | 172.758 | 100% | 88592 | 177.184 | 0 | 0% | 16611.3462 | 33.2227 | 33.2227 | 100% | 13208 | 26.416 | 0 | 0% |  | 13942
4 |  | Material Screening | Sum | 300 | 300 | 700 | 3714.75 | 12.3825 | 12.3825 | 100% | 18200 | 121.3333 | 78 | 155.6% | 1428.75 | 4.7625 | 4.7625 | 100% | 3000 | 20 | 18 | 111.1% |  |  | 15.38%
| HLP | Helpers | days | 300 | 300 | 350 | 3714.75 | 12.3825 | 12.3825 | 100% | 18200 | 60.6667 | 52 | 116.7% | 714.375 | 2.3813 | 2.3813 | 100% | 3000 | 10 | 12 | 83.33% | Lima & Khasab - on hold | 2950
| DZR | Dozer | days | 300 | 300 | 700 | 3714.75 | 12.3825 | 12.3825 | 100% | 18200 | 60.6667 | 26 | 233.3% | 714.375 | 2.3813 | 2.3813 | 100% | 3000 | 10 | 6 | 166.7%
| EXV | Excavator | days | 300 | 300 | 233.3333 | 3714.75 | 12.3825 | 12.3825 | 100% | 18200 | 60.6667 | 78 | 77.78% | 714.375 | 2.3813 | 2.3813 | 100% | 3000 | 10 | 18 | 55.56%
| svl | Shovel | days | 300 | 300 | 233.3333 | 3714.75 | 12.3825 | 12.3825 | 100% | 18200 | 60.6667 | 78 | 77.78% | 714.375 | 2.3813 | 2.3813 | 100% | 3000 | 10 | 18 | 55.56%
5 |  | Aggregate Crushing | Sum | 300 | 300 | 0 | 3714.75 | 12.3825 | 12.3825 | 100% | 0 | 0 | 0 | 0% | 1428.75 | 4.7625 | 4.7625 | 100% | 0 | 0 | 0 | 0% |  |  | 15.38%
| HLP | Helpers | days | 300 | 300 | 0 | 3714.75 | 12.3825 | 12.3825 | 100% |  | 0 | 0 | 0% | 714.375 | 2.3813 | 2.3813 | 100% |  | 0 | 0 | 0% | On Hold due to permission issue
| DZR | Dozer | days | 300 | 300 | 0 | 3714.75 | 12.3825 | 12.3825 | 100% |  | 0 | 0 | 0% | 714.375 | 2.3813 | 2.3813 | 100% | 0 | 0 | 0 | 0%
| EXV | Excavator | days | 300 | 300 | 0 | 3714.75 | 12.3825 | 12.3825 | 100% |  | 0 | 0 | 0% | 714.375 | 2.3813 | 2.3813 | 100% | 0 | 0 | 0 | 0%
| P/S | Power Screen | days | 300 | 300 | 0 | 3714.75 | 12.3825 | 12.3825 | 100% |  | 0 | 0 | 0% | 714.375 | 2.3813 | 2.3813 | 100% | 0 | 0 | 0 | 0%
| DZR | Dozer | days | 300 | 300 | 0 | 3714.75 | 12.3825 | 12.3825 | 100% |  | 0 | 0 | 0% | 714.375 | 2.3813 | 2.3813 | 100% | 0 | 0 | 0 | 0%
6 |  | Preliminaries & Miscellaneous works | Sum |  | 1 | 0.66667 | 3328 | 256 | 256 | 100% |  | 3328 | 0 | 0% | 640 | 640 | 640 | 100% | 640 | 640 | 0 | 0%
| DZR | Dozer | days | 1 | 1 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
| svl | Shovel | days | 1 | 1 | 1 | 208 | 208 | 208 | 100% | 208 | 208 | 208 | 100% | 40 | 40 | 40 | 100% | 40 | 40 | 40 | 100%
| GRD | Grader | days | 1 | 1 | 1 | 26 | 26 | 26 | 100% | 26 | 26 | 26 | 100% | 5 | 5 | 5 | 100% | 5 | 5 | 5 | 100%
| VBR | Vibratory Roller | days | 1 | 1 | 1 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
| EXV | Excavator | days | 1 | 1 |  |  | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
| JCB | JCB | days | 1 | 1 | 1 | 52 | 52 | 52 | 100% | 52 | 52 | 52 | 100% | 10 | 10 | 10 | 100% | 10 | 10 | 10 | 100%
|  | Skid Tyre loader | days | 1 | 1 | 1 | 26 | 26 | 26 | 100% | 26 | 26 | 26 | 100% | 5 | 5 | 5 | 100% | 5 | 5 | 5 | 100%
|  | Mobile crane | days | 1 | 1 | 1 | 52 | 52 | 52 | 100% | 52 | 52 | 52 | 100% | 10 | 10 | 10 | 100% | 10 | 10 | 10 | 100%
|  | Hiab | days | 1 | 1 | 1 | 26 | 26 | 26 | 100% | 26 | 26 | 26 | 100% | 5 | 5 | 5 | 100% | 5 | 5 | 5 | 100%
| HLP | Helpers | days | 1 | 1 | 1 | 234 | 234 | 234 | 100% | 234 | 234 | 234 | 100% | 45 | 45 | 45 | 100% | 45 | 45 | 45 | 100%
| FIX | Steel Fitter | days | 1 | 1 | 0 | 624 | 624 | 624 | 100% | 624 | 624 | 624 | 100% | 120 | 120 | 120 | 100% | 120 | 120 | 120 | 100%
| MAS | Mason | days | 1 | 1 | 0 | 806 | 806 | 806 | 100% | 806 | 806 | 806 | 100% | 155 | 155 | 155 | 100% | 155 | 155 | 155 | 100%
| CAR | Carpenter | days | 1 | 1 | 0 | 1274 | 1274 | 1274 | 100% | 1274 | 1274 | 1274 | 100% | 245 | 245 | 245 | 100% | 245 | 245 | 245 | 100%
3 | ABS | Absentees | Mandays
| SF | Steel Fitter | Mandays
| H | Helpers | Mandays
| SC | Shuttering Carpenter | Mandays
| Scaff | Scaffolder | Mandays
| M | Mason | Mandays
| OP | Operator | Mandays
| RIG | Rigger | Mandays
| HDD | Heavy Duty Driver | Mandays
2
7

## Equipmen (hidden)
BOQ No | Eqp | Qty | Row Labels | Sum of Qty
1 | Back Hoe | 23 | 1 | 82
1 | Bob Cat | 21 | Back Hoe | 24
1.1 | Dozer | 23 | Bob Cat | 24
1.1 | Excavator | 22 | Canter | 2
1.1 | Tipper | 2 | Concrete Mixer | 11
1.1 | Tower light | 10 | Dumper | 1
1.1 | Wheel Loader | 10 | Grader | 1
2.3.6(i)a | Dozer | 106 | Manlift | 2
2.3.6(i)a | Dumper | 3 | Plate Compactor | 1
2.3.6(i)a | Excavator | 316 | Roller | 1
2.3.6(i)a | Grader | 11 | Tipper | 6
2.3.6(i)a | Roller | 11 | Wheel Loader | 9
2.3.6(i)a | Tipper | 2 | 1.1 | 406
2.3.6(i)a | Tower light | 10 | (blank)
2.3.6(i)a | Wheel Loader | 23 | Dozer | 47
2.3.6(i)b | Dozer | 3 | Dumper | 11
2.3.6(i)b | Excavator | 9 | Excavator | 294
2.3.6(i)d | Dozer | 5 | Grader | 10
2.3.6(i)d | Excavator | 19 | Tipper | 2
2.4.6(i) | Dozer | 12 | Tower light | 10
2.4.6(i) | Dumper | 63 | Wheel Loader | 32
2.4.6(i) | Excavator | 28 | 18.3 | 21
2.4.6(i) | Grader | 10 | Excavator | 21
2.4.6(i) | Roller | 10 | 2.3.6(i) | 7
2.4.6(i) | Tipper | 41 | Excavator | 5
2.4.6(i) | Wheel Loader | 12 | Tipper | 1
2.4.6(i) | Dozer | 1 | Wheel Loader | 1
2.3.6(i) | Excavator | 2 | 2.3.6(i)a | 825
3.3.6 (ii) | Wheel Loader | 1 | Dozer | 164
2.3.6(i)c | Dozer | 19 | Dumper | 10
2.3.6(i)c | Excavator | 20 | Excavator | 549
1 | Back Hoe | 1 | Grader | 18
1 | Bob Cat | 3 | Roller | 15
1 | Canter | 2 | Tipper | 33
1 | Concrete Mixer | 11 | Tower light | 10
1 | Dumper | 1 | Wheel Loader | 26
1 | Grader | 1 | 2.3.6(i)b | 35
1 | Manlift | 2 | Dozer | 10
1 | Plate Compactor | 1 | Dumper | 3
1 | Roller | 1 | Excavator | 18
1 | Tipper | 6 | Tipper | 4
1 | Wheel Loader | 9 | 2.3.6(i)c | 75
1.1 | Dozer | 24 | Dozer | 46
1.1 | Excavator | 103 | Excavator | 29
1.1 | (blank) |  | 2.3.6(i)d | 59
2.3.6(i) | Excavator | 3 | Dozer | 5
2.3.6(i) | Tipper | 1 | Excavator | 52
2.3.6(i) | Wheel Loader | 1 | Wheel Loader | 2
2.3.6(i)a | Dozer | 49 | 2.4.6(i) | 770
2.3.6(i)a | Dumper | 7 | Dozer | 112
2.3.6(i)a | Excavator | 208 | Dumper | 116
2.3.6(i)a | Grader | 7 | Excavator | 136
2.3.6(i)a | Roller | 4 | Grader | 24
2.3.6(i)a | Tipper | 31 | Roller | 58
2.3.6(i)a | Wheel Loader | 1 | Tipper | 258
2.4.6(i) | Dozer | 2 | Wheel Loader | 66
2.4.6(i) | Dumper | 1 | 2.4.6(i)a | 94
2.4.6(i) | Excavator | 4 | Dozer | 12
2.4.6(i) | Grader | 3 | Excavator | 27
2.4.6(i) | Roller | 3 | Powerscreen | 25
2.4.6(i) | Tipper | 29 | Roller | 1
2.4.6(i) | Wheel Loader | 2 | Tipper | 6
2.4.6(i) | Excavator | 5 | Wheel Loader | 23
2.4.6(i) | Grader | 3 | 3.3.6 (ii) | 1
2.4.6(i) | Roller | 4 | Wheel Loader | 1
2.4.6(i) | Wheel Loader | 3 | Grand Total | 2375
2.4.6(i)a | Dozer | 2
2.4.6(i)a | Excavator | 11
2.4.6(i)a | Powerscreen | 5
2.4.6(i)a | Roller | 1
2.4.6(i)a | Tipper | 6
2.4.6(i)a | Wheel Loader | 8
2.3.6(i)b | Dozer | 7
2.3.6(i)b | Dumper | 3
2.3.6(i)b | Excavator | 9
2.3.6(i)b | Tipper | 4
1.1 | Dumper | 11
1.1 | Excavator | 169
1.1 | Grader | 10
1.1 | Wheel Loader | 22
2.3.6(i)a | Dozer | 9
2.3.6(i)a | Excavator | 25
2.3.6(i)a | Wheel Loader | 2
2.3.6(i)c | Dozer | 27
2.3.6(i)c | Excavator | 9
2.3.6(i)d | Excavator | 33
2.3.6(i)d | Wheel Loader | 2
2.4.6(i) | Dozer | 97
2.4.6(i) | Dumper | 52
2.4.6(i) | Excavator | 99
2.4.6(i) | Grader | 8
2.4.6(i) | Roller | 41
2.4.6(i) | Tipper | 188
2.4.6(i) | Wheel Loader | 49
2.4.6(i)a | Dozer | 10
2.4.6(i)a | Excavator | 16
2.4.6(i)a | Powerscreen | 20
2.4.6(i)a | Wheel Loader | 15
18.3 | Excavator | 21

## Manpower (hidden)
S.No | Description | Qty | Row Labels | Sum of Qty
Khasab |  |  | 1 | 559
1 | Carpenter | 64 | Carpenter | 157
1 | Foreman | 22 | Foreman | 22
1 | Helper | 21 | Helper | 111
1 | Mason | 40 | Mason | 125
1 | Steel Fixer | 60 | Steel Fixer | 144
1.1 | Foreman | 22 | 1.1 | 227
1.1 | Helper | 22 | Chargehand | 14
2.3.6(i)a | Chargehand | 37 | Foreman | 37
2.3.6(i)a | Foreman | 35 | Helper | 120
2.3.6(i)a | Helper | 229 | Supervisor | 56
2.3.6(i)a | Supervisor | 37 | 2.3.6(i) | 5
2.3.6(i)b | Helper | 5 | Foreman | 1
2.3.6(i)b | Supervisor | 4 | Helper | 2
2.3.6(i)d | Helper | 9 | Supervisor | 2
2.3.6(i)d | Supervisor | 3 | 2.3.6(i)a | 434
2.4.6(i) | Helper | 29 | Chargehand | 43
2.4.6(i) | Supervisor | 19 | Foreman | 58
2.3.6(i) | Supervisor | 1 | Helper | 249
2.3.6(i)c | Helper | 15 | Supervisor | 84
2.3.6(i)c | Supervisor | 9 | 2.3.6(i)b | 112
Lima |  |  | Foreman | 24
1 | Carpenter | 93 | Helper | 83
1 | Helper | 90 | Supervisor | 5
1 | Mason | 85 | 2.3.6(i)c | 24
1 | Steel Fixer | 84 | Helper | 15
1.1 | Chargehand | 14 | Supervisor | 9
1.1 | Helper | 61 | 2.3.6(i)d | 12
1.1 | Supervisor | 34 | Helper | 9
2.3.6(i) | Foreman | 1 | Supervisor | 3
2.3.6(i) | Helper | 2 | 2.4.6(i) | 114
2.3.6(i) | Supervisor | 1 | Foreman | 15
2.3.6(i)a | Chargehand | 6 | Helper | 33
2.3.6(i)a | Foreman | 21 | Mason | 21
2.3.6(i)a | Helper | 18 | Supervisor | 45
2.3.6(i)a | Supervisor | 45 | 2.4.6(i)a | 14
2.4.6(i) | Foreman | 1 | Helper | 12
2.4.6(i) | Supervisor | 4 | Supervisor | 2
2.4.6(i) | Foreman | 2 | Daba
2.4.6(i) | Helper | 1 | (blank)
2.4.6(i) | Supervisor | 1 | Khasab
2.4.6(i)a | Helper | 12 | (blank)
2.4.6(i)a | Supervisor | 2 | Lima
2.3.6(i)b | Foreman | 3 | (blank)
2.3.6(i)b | Helper | 15 | Grand Total | 1501
2.3.6(i)b | Supervisor | 1
Daba
1.1 | Foreman | 15
1.1 | Helper | 37
1.1 | Supervisor | 22
2.3.6(i)a | Foreman | 2
2.3.6(i)a | Helper | 2
2.3.6(i)a | Supervisor | 2
2.3.6(i)b | Foreman | 21
2.3.6(i)b | Helper | 63
2.4.6(i) | Foreman | 12
2.4.6(i) | Helper | 3
2.4.6(i) | Mason | 21
2.4.6(i) | Supervisor | 21

## Equp
Access road
Description | Excavator |  |  | Dozer |  |  | Helpers
| no | Days | Qty | no | Days | Qty | no | Days | Qty
Khasab -Day Shift | 2 | 6 | 12 | 1 | 6 | 6 | 1 | 6 | 6
Khasab -Night Shift | 2 | 6 | 12 | 1 | 6 | 6 | 1 | 6 | 6
Lima | 4 | 6 | 24 | 1 | 6 | 6 | 2 | 6 | 12 | 3
Daba | 3 | 6 | 18 | 1 | 6 | 6 | 2 | 6 | 12
Total For the Week | 11 |  | 66 | 4 |  | 24 | 6 |  | 36
Up to Previous week | 11 |  | 220 | 4 |  | 80 | 6 |  | 120 | [6 empty] | 6.5
Deduction(B/D, N/O)
Cumm. For the month |  |  | 286 |  |  | 104 |  |  | 156
Excavation/Over Burden Removal/Mechanical Excavation
Description | Excavator |  |  | Dozer |  |  | Helpers
| no | Days | Qty | no | Days | Qty | no | Days | Qty
Khasab -Day Shift | 31 | 6 | 186 | 10 | 6 | 60 | 10 | 6 | 60
Khasab -Night Shift | 1 | 6 | 6 | 1 | 6 | 6 | 2 | 6 | 12
Lima | 39 | 6 | 234 | 9 | 6 | 54 | 5 | 6 | 30
Daba | 4 | 6 | 24 | 3 | 6 | 18 | 10 | 6 | 60 |  |  | 204
Total For the Week | 75 |  | 450 | 23 |  | 138 | 27 |  | 162
Up to Previous week | 75 |  | 1500 | 23 |  | 460 | 27 |  | 540
Deduction(B/D, N/O)
Cumm. For the month |  |  | 1950 |  |  | 598 |  |  | 702 | [12 empty] | 210
To Rawasi
Embankment Filling
Description | Excavator |  |  | Dozer |  |  | Grader |  |  | Roller |  |  | Tippers |  |  | Dumpers |  |  | Water Tankers |  |  | Helpers |  |  | Wheel Loaders
| no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty
Khasab | 3 | 6 | 18 | 1 | 6 | 6 | 1 | 6 | 6 | 1 | 6 | 6 | 3 | 6 | 18 | 2 | 6 | 12 |  | 6 | 0 | 2 | 6 | 12 |  | 6 | 0
Lima |  | 6 | 0 | 1 | 6 | 6 | 2 | 6 | 12 | 2 | 6 | 12 | 6 | 6 | 36 | 2 | 6 | 12 |  | 6 | 0 | 3 | 6 | 18 |  | 6 | 0
Daba |  | 6 | 0 | 1 | 6 | 6 | 1 | 6 | 6 | 2 | 6 | 12 | 11 | 6 | 66 | 4 | 6 | 24 |  | 6 | 0 | 2 | 6 | 12 |  | 6 | 0
Total For the Week | 3 |  | 18 | 3 |  | 18 | 4 |  | 24 | 5 |  | 30 | 20 |  | 120 | 8 |  | 48 | 0 |  | 0 | 7 |  | 42 | 0 |  | 0
Up to Previous week | 3 |  | 60 | 3 |  | 60 | 4 |  | 80 | 5 |  | 100 | 20 |  | 400 | 8 |  | 160 | 0 |  | 0 | 7 |  | 140 | 0 |  | 0
Deduction(B/D, N/O) | [14 empty] | -6.3
Cumm. For the month |  |  | 78 |  |  | 78 |  |  | 104 |  |  | 130 |  |  | 513.7 |  |  | 208 |  |  | 0 |  |  | 182 |  |  | 0
Material Screening
Description | Wheel loder |  |  | Dozer |  |  | Grader |  |  | Roller |  |  | Tippers |  |  | Excavator |  |  | Water Tankers |  |  | Helpers
| no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty
Khasab | 1 | 6 | 6 | 1 | 6 | 6 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 | 1 | 6 | 6 |  | 6 | 0 |  | 6 | 0
Lima | 1 | 6 | 6 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 | 1 | 6 | 6 |  | 6 | 0 |  | 6 | 0
Daba | 1 | 6 | 6 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 | 1 | 6 | 6 |  | 6 | 0 | 2 | 6 | 12
Total For the Week | 3 |  | 18 | 1 |  | 6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 18 | 0 |  | 0 | 2 |  | 12
Up to Previous week | 3 |  | 60 | 1 |  | 20 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  | 60 | 0 |  | 0 | 2 |  | 40
Deduction(B/D, N/O)
Cumm. For the month |  |  | 78 |  |  | 26 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 78 |  |  | 0 |  |  | 52
Aggregate Crushing
Description | Excavator |  |  | Dozer |  |  | Crhser |  |  | P/S |  |  | Tippers | [8 empty] | Helpers
| no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty | no | Days | Qty |  |  |  | no | Days | Qty | no | Days | Qty
Khasab |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  |  |  |  | 6 | 0 |  | 6 | 0
Lima |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  |  |  |  | 6 | 0 |  | 6 | 0
Daba |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  | 6 | 0 |  |  |  |  | 6 | 0 |  | 6 | 0
Total For the Week | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0
Up to Previous week | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0
Deduction(B/D, N/O)
Cumm. For the month |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 |  |  | 0
Excavator | 89 |  |  | 29 | [5 empty] | 3 |  |  | 0 |  |  | 1 |  |  | 0 |  |  | 0
Excv
Khasab | 37 |  |  | 13
Lima | 44 |  |  | 11
Daba | 8 |  |  | 5
| 89 |  |  | 29

## Sheet2 (hidden)
|  | Khasab | Lima | Daba | Total
| Acces raod |  | 1 | 2 | 3
| Excavation | 16 | 5 | 1 | 22
25
Cummulative |  | Khasab | Lima | Daba | Total
Access road
| Helper | 20 | 12 | 7 | 39
| Excavator | 18 | 41 | 28 | 87
| Dozer | 18 | 16 | 11 | 45
Excavation
| Helper | 106
| Excavator | 93
Dozer
Wheel loader