## Sheet1 (F) (2)
Project AI Agent
S No | Inputs: | Tools + Techniques | Outputs:
1 | •Supervisor daily executed work •Resource deployment •Photographs, •Next day plan •Concerns/Remarks • Weather data •Monthly/daily Supervisor plan |  | •Daily progress report (DPR)- Internal/external -roll up to weekly/monthly •Daily Commodity summary-roll up to weekly/monthly
2 | •Manpower Productivity norms - activity wise •Equipment Productivity norms - activity wise •Resource deployment |  | • Resource Capacity Utilization ♦Equipment productivity ♦Manpower Productivity
3 | •Daily work executed by Supervisor w.r.t budgeted unit rates •Daily resource deployment (Manpower & Machinery) •Equipment/ Manpower unit Rates •Material Unit rates •Sub-contract unit rates •Resource deployment •Material consumption by supervisor/Store keeper |  | • Daily Balance Sheet (DBS) for the day- roll up to weekly/monthly ♦Supervisor wise ♦Roll up to Engineer/Site Manager level ♦ Roll up to Project Manager • Material consumption report
4 | •Material unit rates •Equipment/ Manpower unit rates •Sub-contract unit rates •BOQ rates & Budgeted unit rates •Resource deployment (Men & Machinery) •Daily work executed by Supervisor |  | Costing: •Activity costing report •Variance report w.r.t budgeted unit rates
5 | •Material unit rates •Equipment/ Manpower unit rates •Sub-contract unit rates •BOQ rates & Budgeted unit rates •Resource deployment (Men & Machinery) •Daily work executed by Supervisor |  | Performance (Daily/Weekly/Monthly): •Profit & Loss (P&L) w.r.t budgeted unit rates •Profit & Loss (P&L) w.r.t BOQ rates
6 | Above inputs & outputs Approved Drawings, Specifications, Method statements, ITP & Project Plans |  | FAQs & Chatbot
| Data input mode (Mobile/Laptop): |  | Data output mode (Mobile/Laptop):
| Voice note |  | Text & Graphical representation
Photos
attachments
text
WhatsApp
Pilot project: No.of Users Supervisors-4 Nos Site Engineers-2 Nos Project Control-1 No PM-1 No

## Access-Input
Input Matrix
1 | Daily executed work | Data posting | Editing data | View | Report Download
| Supervisor | TRUE | FALSE | TRUE | TRUE | Note: Data entry done by the Supervisor, can be edited by Project Controller/Respective Engineer , if any anomaly.
| Engineer | FALSE | TRUE | TRUE | TRUE
| Project Control Engineer | FALSE | TRUE | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE | TRUE | TRUE
| Site Manager | FALSE | TRUE | TRUE | TRUE
| Project Manager | FALSE | FALSE | TRUE | TRUE
2 | Resource (Manpower & Equipment) deployment for the day
| Supervisor | TRUE | FALSE | TRUE | TRUE
| Engineer | TRUE | TRUE | TRUE | TRUE
| Project Control Engineer | FALSE | TRUE | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE | TRUE | TRUE
| Site Manager | FALSE | TRUE | TRUE | TRUE
| Project Manager | FALSE | FALSE | TRUE | TRUE
3 | Photographs
| Supervisor | TRUE | FALSE | TRUE | TRUE
| Engineer | TRUE | FALSE | TRUE | TRUE
| Project Control Engineer | FALSE | TRUE | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE | TRUE | TRUE
| Site Manager | TRUE | TRUE | TRUE | TRUE
| Project Manager | FALSE | FALSE | TRUE | TRUE
4 | Next day Plan
| Supervisor | TRUE | TRUE
| Engineer | TRUE | FALSE | TRUE | FALSE
| Project Control Engineer | FALSE | TRUE | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE | TRUE | FALSE
| Site Manager | FALSE | TRUE | TRUE | TRUE
| Project Manager | FALSE | FALSE | TRUE | TRUE
5 | Concerns/Remarks
| Supervisor | TRUE | TRUE
| Engineer | TRUE | TRUE | TRUE | FALSE
| Project Control Engineer | FALSE | TRUE | TRUE | TRUE
| Quantity Surveyor | FALSE | TRUE | TRUE | FALSE
| Site Manager | FALSE | TRUE | TRUE | TRUE
| Project Manager | FALSE | TRUE | TRUE | TRUE
6 | Weather Data
| Supervisor | TRUE | TRUE
| Engineer | TRUE | TRUE
| Project Control Engineer | FALSE | TRUE
| Quality Engineer | TRUE | TRUE
| Site Manager | FALSE | TRUE
| Project Manager | FALSE | FALSE
7 | Monthly plan
| Supervisor | TRUE | TRUE
| Engineer | TRUE | TRUE
| Project Control Engineer | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE
| Site Manager | FALSE | TRUE
| Project Manager | FALSE | FALSE
8 | Manpower & Equipment Productivity Norms
| Supervisor | FALSE | FALSE
| Engineer | FALSE | FALSE
| Project Control Engineer | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE
| Site Manager | FALSE | FALSE
| Project Manager | FALSE | FALSE
8 | Manpower, Equipment & Material Unit Rates
| Supervisor | FALSE | FALSE
| Engineer | FALSE | FALSE
| Project Control Engineer | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE
| Site Manager | FALSE | FALSE
| Project Manager | FALSE | FALSE
9 | Sub-contract Unit Rates
| Supervisor | FALSE | FALSE
| Engineer | FALSE | FALSE
| Project Control Engineer | FALSE | TRUE
| Quantity Surveyor | TRUE | TRUE
| Site Manager | FALSE | FALSE
| Project Manager | FALSE | FALSE
10 | Sub-contract Unit Rates
| Supervisor | FALSE | FALSE
| Engineer | FALSE | FALSE
| Project Control Engineer | FALSE | TRUE
| Quantity Surveyor | TRUE | TRUE
| Site Manager | FALSE | FALSE
| Project Manager | FALSE | FALSE
11 | Material consumption
| Supervisor | TRUE | TRUE
| Engineer | FALSE | FALSE
| Project Control Engineer | FALSE | TRUE
| Quantity Surveyor | FALSE | TRUE
| Store keeper | TRUE | TRUE
| Project Manager | FALSE | FALSE
12 | BOQ & Budgeted Unit rates
| Supervisor | FALSE | FALSE
| Engineer | FALSE | FALSE
| Project Control Engineer | TRUE | TRUE
| Quantity Surveyor | TRUE | TRUE
| Store keeper | FALSE | FALSE
| Project Manager | FALSE | FALSE
13 | Approved Drawings
| Supervisor | FALSE | FALSE
| Engineer | FALSE | FALSE
| Project Control Engineer | FALSE | FALSE
| Quantity Surveyor | TRUE | TRUE
| Design Coordinator | TRUE | TRUE
| Project Manager | FALSE | FALSE
14 | Specifications, Method statements, ITP & Project Plans
| Supervisor | FALSE | FALSE
| Engineer | FALSE | FALSE
| Project Control Engineer | TRUE | TRUE
| Quality Engineer | TRUE | TRUE
| Store keeper | FALSE | FALSE
| Project Manager | FALSE | FALSE
14 | Voice Notes, text, attachments, WhatsApp messages
| Supervisor | TRUE | TRUE
| Engineer | TRUE | TRUE
| Project Control Engineer | TRUE | TRUE
| Quality Engineer | TRUE | TRUE
| Site Manager | TRUE | TRUE
| Project Manager | TRUE | TRUE

## Access-Output
Output Matrix
1 | DPR | Data posting | Editing data | View | Report Download
| Supervisor | FALSE | FALSE | TRUE | TRUE | Note: Data entry done by the Supervisor, can be edited by Project Controller , if any anomaly.
| Engineer | FALSE | FALSE | TRUE | TRUE
| Project Control Engineer | FALSE | FALSE | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE | TRUE | TRUE
| Site Manager | FALSE | FALSE | TRUE | TRUE
| Project Manager | FALSE | FALSE | TRUE | TRUE
2 | Capacity Utilization
| Supervisor | FALSE | FALSE | TRUE | TRUE
| Engineer | FALSE | FALSE | TRUE | TRUE
| Project Control Engineer | FALSE | FALSE | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE | TRUE | TRUE
| Site Manager | FALSE | FALSE | TRUE | TRUE
| Project Manager | FALSE | FALSE | TRUE | TRUE
3 | Daily Balance Sheet (DBS)
| Supervisor | FALSE | FALSE | TRUE | TRUE
| Engineer | FALSE | FALSE | TRUE | TRUE
| Project Control Engineer | FALSE | FALSE | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE | TRUE | TRUE
| Site Manager | FALSE | FALSE | TRUE | TRUE
| Project Manager | FALSE | FALSE | TRUE | TRUE
4 | Activity Costing & Variance Report
| Engineer | FALSE | FALSE | TRUE | FALSE
| Project Control Engineer | FALSE | FALSE | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE | TRUE | TRUE
| Site Manager | FALSE | FALSE | TRUE | TRUE
| Project Manager | FALSE | FALSE | TRUE | TRUE
5 | Performance (P&L)
| Engineer | FALSE | FALSE | TRUE | TRUE
| Project Control Engineer | FALSE | FALSE | TRUE | TRUE
| Quantity Surveyor | FALSE | FALSE | TRUE | TRUE
| Site Manager | FALSE | FALSE | TRUE | TRUE
| Project Manager | FALSE | FALSE | TRUE | TRUE